ENGINEERING

ServicePro Delivery Roadmap

1. Current State

Publication edition  |  2026-08-03

# Document Control

| Purpose | Enterprise platform overview and buyer evaluation reference |
| --- | --- |
| Audience | Business leaders, platform administrators, evaluators, partners, and technical stakeholders |
| Scope | Capabilities, architecture, security, deployment, adoption, outcomes, and terminology |
| Source | ServicePro repository documentation; technical meaning preserved |

Use the linked table of contents below or Word's Navigation Pane to move through this document.

# Table of Contents

Document Control

2. Workstream Overview

3. Workstream Details

3.1 Production Hardening (Weeks 1–4)

3.2 Developer Experience (Weeks 2–6)

3.3 Frontend Modernization (Weeks 4–10)

3.4 API Architecture (Weeks 6–14)

3.5 Data Platform (Weeks 8–16)

3.6 Observability (Weeks 10–18)

3.7 Security Hardening (Weeks 4–12)

3.8 Feature Completion (Ongoing)

4. Resource Requirements

4.1 Infrastructure Costs (Monthly)

4.2 Scaling Thresholds

5. Milestone Schedule

6. Risk Register

7. Decision Log

Version: 8.0.0-alpha.1 Date: July 2026 Planning Horizon: 6 months

ServicePro is a functional alpha with strong feature coverage for field service operations. The platform serves real tenants (Aqua Pro Plumbing, C & D Landscaping) but runs on free-tier infrastructure without production hardening. The gap between "working code" and "production-grade platform" is the focus of this roadmap.

# 2. Workstream Overview

| # | Workstream | Priority | Timeline | Objective |
| --- | --- | --- | --- | --- |
| 1 | Production Hardening | Critical | Weeks 1–4 | Eliminate service reliability risks |
| 2 | Developer Experience | High | Weeks 2–6 | CI/CD, testing, type safety |
| 3 | Frontend Modernization | High | Weeks 4–10 | Performance, maintainability, UX |
| 4 | API Architecture | Medium | Weeks 6–14 | Framework adoption, router refactor |
| 5 | Data Platform | Medium | Weeks 8–16 | Backups, monitoring, connection pooling |
| 6 | Observability | Medium | Weeks 10–18 | Error tracking, metrics, alerting |
| 7 | Security Hardening | High | Weeks 4–12 | Scanning, rotation, penetration testing |
| 8 | Feature Completion | Ongoing | Weeks 1–24 | Customer portal, mobile, admin UI |

# 3. Workstream Details

## 3.1 Production Hardening (Weeks 1–4)

Goal: Make the platform reliable enough for paying customers.

| Task | Effort | Impact |
| --- | --- | --- |
| Upgrade Render API to Starter plan ($7/mo) | 1 hour | Eliminates 50s cold starts |
| Upgrade Supabase to Pro ($25/mo) | 1 hour | Daily backups, no pause, 8 GB |
| Add health check alerting (UptimeRobot or similar) | 2 hours | Know when service is down |
| Configure proper CORS for production domain only | 1 hour | Tighten security surface |
| Add package-lock.json to root and enforce npm ci | 1 hour | Reproducible builds |
| Move JWT_SECRET to environment variable (not generate) | 1 hour | Survives redeploy |
| Document recovery procedure for DB restoration | 4 hours | Runbook for incidents |

Exit Criteria: API responds in <2s on first request, database has daily backups, alerting notifies on downtime.

## 3.2 Developer Experience (Weeks 2–6)

Goal: Prevent regressions, enforce quality, enable safe collaboration.

| Task | Effort | Impact |
| --- | --- | --- |
| Add TypeScript --noEmit check to CI | 2 hours | Catch type errors before deploy |
| Run test suite in CI (even if some fail, report) | 4 hours | Visibility into test health |
| Add ESLint with recommended rules | 4 hours | Code consistency |
| Enable branch protection on main | 30 min | Require PR for changes |
| Add PR template with checklist | 1 hour | Structured review |
| Set up Playwright for E2E smoke tests | 8 hours | Critical path verification |
| Create .env.local.example for onboarding | 1 hour | New developer setup |
| Document local development setup in README | 2 hours | Reduce onboarding friction |

Exit Criteria: CI blocks PRs with type errors, at least 5 E2E tests covering login/jobs/storefront, branch protection enabled.

## 3.3 Frontend Modernization (Weeks 4–10)

Goal: Improve performance, reduce component complexity, establish design system.

| Task | Effort | Impact |
| --- | --- | --- |
| Break StorefrontBuilder into 5–8 sub-components | 12 hours | Maintainability |
| Break PublicStorefront into section components | 8 hours | Testability |
| Extract shared UI primitives (Button, Input, Modal, Card) | 16 hours | Consistency |
| Remove CSS !important overrides — use proper specificity | 8 hours | Predictable styling |
| Add component-level Storybook or similar catalog | 8 hours | Visual regression |
| Implement proper loading/error states for all data fetches | 8 hours | UX polish |
| Add skeleton screens for slow API responses | 4 hours | Perceived performance |
| Audit accessibility (WCAG 2.1 AA) for core flows | 8 hours | Compliance |

Exit Criteria: No component exceeds 400 lines, shared UI library covers 80% of patterns, no !important in stylesheets.

## 3.4 API Architecture (Weeks 6–14)

Goal: Replace fragile raw HTTP routing with maintainable framework.

| Task | Effort | Impact |
| --- | --- | --- |
| Evaluate Express vs. Fastify (recommend Fastify for perf) | 4 hours | Informed decision |
| Extract route groups from router.js into modular files | 16 hours | Maintainability |
| Adopt chosen framework incrementally (adapter pattern) | 24 hours | Modern middleware |
| Remove or lazy-load Phase 9–45 stub modules | 8 hours | Faster startup |
| Standardize error response format across all routes | 8 hours | API consistency |
| Generate OpenAPI spec from route definitions | 8 hours | Documentation |
| Add request/response validation (Zod or Joi) | 16 hours | Input safety |

Exit Criteria: Router.js under 200 lines, all routes registered via framework router, startup time under 3 seconds.

## 3.5 Data Platform (Weeks 8–16)

Goal: Production-grade database operations.

| Task | Effort | Impact |
| --- | --- | --- |
| Implement connection pooling (Supabase Vibes or PgBouncer) | 4 hours | Connection efficiency |
| Add slow query logging (pg_stat_statements) | 4 hours | Performance visibility |
| Set up automated backup verification (restore to temp) | 8 hours | Backup confidence |
| Add database migration CI check (dry-run) | 4 hours | Prevent broken migrations |
| Implement proper migration versioning (sequential numbered) | 8 hours | Schema history |
| Add tenant data isolation tests | 8 hours | Security verification |
| Plan upgrade path from free tier when needed | 2 hours | Capacity planning |

Exit Criteria: Connection pooling active, slow queries logged, backup restore verified monthly.

## 3.6 Observability (Weeks 10–18)

Goal: See what's happening in production without SSH access.

| Task | Effort | Impact |
| --- | --- | --- |
| Add Sentry for error tracking (free tier: 5K events/mo) | 4 hours | Error visibility |
| Add structured JSON logging | 8 hours | Log searchability |
| Implement request duration tracking | 4 hours | Performance baseline |
| Add database query timing | 4 hours | Bottleneck detection |
| Set up Render metrics dashboard | 2 hours | Resource monitoring |
| Add custom health metrics (tenant count, job volume) | 4 hours | Business metrics |
| Configure alerting thresholds | 4 hours | Proactive notification |

Exit Criteria: All unhandled errors captured, P95 latency visible, alerts for error spike and downtime.

## 3.7 Security Hardening (Weeks 4–12)

Goal: Close security gaps before acquiring more customers.

| Task | Effort | Impact |
| --- | --- | --- |
| Add npm audit to CI with failure on high severity | 2 hours | Dependency safety |
| Implement JWT secret rotation mechanism | 8 hours | Secret hygiene |
| Add CSRF protection for state-changing endpoints | 8 hours | Request forgery prevention |
| Implement rate limiting per tenant (not just global) | 4 hours | Abuse prevention |
| Add input sanitization audit for all user inputs | 8 hours | Injection prevention |
| Enable Supabase Row Level Security for shared tables | 12 hours | Defense in depth |
| Schedule quarterly dependency update review | 2 hours | Maintenance cadence |
| Document security incident response procedure | 4 hours | Readiness |

Exit Criteria: Zero high-severity npm audit findings, per-tenant rate limiting active, RLS on shared tables.

## 3.8 Feature Completion (Ongoing)

Goal: Complete customer-facing features that drive revenue.

| Feature | Effort | Priority |
| --- | --- | --- |
| Customer Portal — full self-service (booking, payments, history) | 40 hours | High |
| Admin UI — complete platform management interface | 24 hours | High |
| Mobile responsive improvements (remaining pages) | 16 hours | Medium |
| Email notifications (transactional via SendGrid/Resend) | 12 hours | High |
| Payment processing integration (Stripe) | 20 hours | High |
| SMS notifications (Twilio) | 8 hours | Medium |
| Reporting export to PDF/Excel | 8 hours | Medium |
| Multi-user support per workspace | 12 hours | Medium |

# 4. Resource Requirements

## 4.1 Infrastructure Costs (Monthly)

| Service | Current | Recommended | Cost |
| --- | --- | --- | --- |
| Render API | Free | Starter | $7/mo |
| Render DB | Free | — (use Supabase) | $0 |
| Supabase | Free | Pro | $25/mo |
| Cloudflare Workers | Free | Free | $0 |
| Sentry | — | Free tier | $0 |
| UptimeRobot | — | Free tier | $0 |
| Total | $0 | — | $32/mo |

## 4.2 Scaling Thresholds

| Trigger | Action | Cost Impact |
| --- | --- | --- |
| >5 tenants active | Upgrade Render to Standard ($25/mo) | +$18/mo |
| >50 concurrent users | Add Redis caching | +$15/mo |
| >1 GB database | Supabase already Pro | Included |
| >100 tenants | Evaluate multi-instance API | +$50/mo |

# 5. Milestone Schedule

| Milestone | Target | Key Deliverables |
| --- | --- | --- |
| M1: Stable Production | Week 4 | Paid hosting, backups, alerting, no cold starts |
| M2: CI/CD Complete | Week 6 | Tests in CI, branch protection, type checking |
| M3: Security Baseline | Week 12 | Audit clean, RLS, rate limiting, rotation |
| M4: Framework Migration | Week 14 | Fastify/Express adopted, router refactored |
| M5: Frontend V2 | Week 10 | Component library, no overrides, accessible |
| M6: Observability | Week 18 | Full error tracking, metrics, alerting |
| M7: Feature Complete | Week 24 | Customer portal, payments, email, mobile |

# 6. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Free tier service outage during customer demo | High | High | Upgrade to paid plans (M1) |
| Database pause loses customer data | Medium | Critical | Supabase Pro + backup verification |
| Regression deployed to production | High | Medium | CI test gating (M2) |
| Security breach via unvalidated input | Medium | Critical | Input validation audit (M3) |
| Developer confusion from 14K file count | High | Low | Documentation, .gitignore cleanup |
| Router.js becomes unmaintainable | High | Medium | Framework migration (M4) |
| Customer-visible errors with no alerting | High | Medium | Sentry integration (M6) |

# 7. Decision Log

| Decision | Rationale | Date |
| --- | --- | --- |
| Stay on Supabase (not Render DB) | Better free tier, familiar, pooling built-in | July 2026 |
| Static export for frontend | Cloudflare Workers = fast, free, global CDN | July 2026 |
| No Express/Fastify yet | Working system, refactor after stabilization | July 2026 |
| Phase 9–45 remain scaffolded | Future roadmap, don't delete, but lazy-load | July 2026 |
| Monorepo stays (no microservices yet) | Single deploy target, simple, 2 tenants | July 2026 |